## Slide 1
Data Analysis: Project Budget to Actual

## Slide 2
Upon reviewing the allocated time for each project, it is evident that Project D received the highest number of assigned hours, while Project B was allocated the least. It is worth noting that all projects exhibited minimal disparities between the actual and budgeted hours.
Nevertheless, Projects A, B, and C exceeded their respective budgeted hours, while Projects D and E remained within their budgeted hours. Project C incurred the highest negative variance, indicating additional hours beyond the allocated budget, whereas Project E showcased the most positive variance, implying a surplus of hours.
In aggregate, the company expended an additional 120 hours across these five projects.
Project Name | Total | ActualTotal
Project A | 2160 | 2364
Project B | 1350 | 1458
Project C | 2760 | 3078
Project D | 3300 | 3156
Project E | 2580 | 2214
Grand Total | 12150 | 12270
Chart: Over/Under Budget Hours
| Project A | Project B | Project C | Project D | Project E
Total | 2160 | 1350 | 2760 | 3300 | 2580
ActualTotal | 2364 | 1458 | 3078 | 3156 | 2214

## Slide 3
A consistent pattern emerges when examining the correlation between the over/under hours and the final cost, as the latter is directly influenced by the budgeted hours.
Notably, Project D and E remained under budget, with Project D having the highest budget allocation and Project B the lowest.
Values | Project A | Project B | Project C | Project D | Project E | Grand Total
BudgetTotal | $ 153,600 | $ 131,100 | $ 216,000 | $ 291,000 | $ 174,480 | $ 966,180
ActualTotal | $ 168,150 | $ 135,600 | $ 243,300 | $ 271,500 | $ 138,240 | $ 956,790
Chart: Over/Under Cost
| Project A | Project B | Project C | Project D | Project E
BudgetTotal | 153600 | 131100 | 216000 | 291000 | 174480
ActualTotal | 168150 | 135600 | 243300 | 271500 | 138240

## Slide 4
Over/Under Personnel Performance
Row Labels | Max of Cost $ / hr | TotalBudget | TotalActual
Crystal | 120 | 900 | 900
Erica | 140 | 960 | 900
Gail | 50 | 930 | 1026
George | 60 | 960 | 1200
Inigo | 95 | 960 | 660
Jenny | 75 | 960 | 1020
Jim | 90 | 960 | 1050
Larry | 88 | 960 | 480
Monique | 105 | 960 | 1200
Sarah | 75 | 960 | 1020
Sondra | 45 | 960 | 960
Stanley | 50 | 720 | 864
Tom | 35 | 960 | 990
Grand Total | 140 | 12150 | 12270
Chart: 
| Crystal | Erica | Gail | George | Inigo | Jenny | Jim | Larry | Monique | Sarah | Sondra | Stanley | Tom
TotalBudget | 900 | 960 | 930 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 720 | 960
TotalActual | 900 | 900 | 1026 | 1200 | 660 | 1020 | 1050 | 480 | 1200 | 1020 | 960 | 864 | 990

## Slide 5: Sondra and Crystal adhered precisely to their assigned hours, effectively utilizing the designated time. Conversely, Erica, Inigo, and Larry demonstrated suboptimal performance, falling short of the expected productivity levels. In contrast, the remaining eight employees surpassed the budgeted hours, showcasing commendable work ethic. Remarkably, ten out of thirteen employees were assigned a uniform 960-hour workload, with Erica, despite being compensated the highest wage per hour, exhibiting underperformance. Larry and Inigo, both receiving above-average hourly wages, also failed to meet the expected level of productivity. Monique and George stood out among their peers, surpassing all other employees by working a total of 1200 hours. Notably, Larry consistently demonstrated lower performance compared to the rest of the workforce. Interestingly, Tom, despite having the lowest hourly wage, exceeded the expectations and outperformed many of his colleagues.

## Slide 6
Row Labels | Max of Cost $ / hr | BudgetTotalCost | ActualTotalCost
Crystal | $ 120 | $ 108,000 | $ 108,000.0
Erica | $ 140 | $ 134,400 | $ 126,000.0
Gail | $ 50 | $ 46,500 | $ 51,300.0
George | $ 60 | $ 57,600 | $ 72,000.0
Inigo | $ 95 | $ 91,200 | $ 62,700.0
Jenny | $ 75 | $ 72,000 | $ 76,500.0
Jim | $ 90 | $ 86,400 | $ 94,500.0
Larry | $ 88 | $ 84,480 | $ 42,240.0
Monique | $ 105 | $ 100,800 | $ 126,000.0
Sarah | $ 75 | $ 72,000 | $ 76,500.0
Sondra | $ 45 | $ 43,200 | $ 43,200.0
Stanley | $ 50 | $ 36,000 | $ 43,200.0
Tom | $ 35 | $ 33,600 | $ 34,650.0
Grand Total | $ 140 | $ 966,180 | $ 956,790.0

## Slide 7: Over/Under Personnel cost
Chart: 
| Crystal | Erica | Gail | George | Inigo | Jenny | Jim | Larry | Monique | Sarah | Sondra | Stanley | Tom
BudgetTotalCost | 108000 | 134400 | 46500 | 57600 | 91200 | 72000 | 86400 | 84480 | 100800 | 72000 | 43200 | 36000 | 33600
ActualTotalCost | 108000 | 126000 | 51300 | 72000 | 62700 | 76500 | 94500 | 42240 | 126000 | 76500 | 43200 | 43200 | 34650

## Slide 8: In accordance with the trend of over/under personnel performance hours, Crystal and Sondra received compensation precisely equivalent to their assigned hours. Erica, Inigo, and Larry, on the other hand, received remuneration corresponding to the budgeted cost. Interestingly, despite their lower performance levels, certain employees earned higher incomes due to disparities in their hourly wage. Erica, in particular, received the highest compensation despite her underperformance. Among the employees, Monique exhibited the most significant positive variance, while Inigo demonstrated the highest negative variance between the budgeted and actual costs. Notably, Tom earned the lowest income from the projects due to his lower hourly wage. In summary, it can be concluded that the employees' payroll is primarily influenced by their hourly rate rather than their working hours.

## Slide 9: Task Comparison
Row Labels | BudgetTotalHour | ActualTotalHour | Percentage Diff
AT1 | 1800 | 1992 | -11%
AT2 | 180 | 180 | 0%
AT3 | 180 | 192 | -7%
BT1 | 420 | 516 | -23%
BT2 | 510 | 495 | 3%
BT3 | 420 | 447 | -6%
CT1 | 1140 | 1140 | 0%
CT2 | 660 | 942 | -43%
CT3 | 480 | 477 | 1%
CT4 | 180 | 222 | -23%
CT5 | 300 | 297 | 1%
DT1 | 1380 | 1080 | 22%
DT2 | 840 | 882 | -5%
DT3 | 720 | 792 | -10%
DT4 | 360 | 402 | -12%
ET1 | 480 | 552 | -15%
ET2 | 2100 | 1662 | 21%
Grand Total | 12150 | 12270 | -1%

## Slide 10
Chart: Task Comparison
| AT1 | AT2 | AT3 | BT1 | BT2 | BT3 | CT1 | CT2 | CT3 | CT4 | CT5 | DT1 | DT2 | DT3 | DT4 | ET1 | ET2
BudgetTotalHour | 1800 | 180 | 180 | 420 | 510 | 420 | 1140 | 660 | 480 | 180 | 300 | 1380 | 840 | 720 | 360 | 480 | 2100
ActualTotalHour | 1992 | 180 | 192 | 516 | 495 | 447 | 1140 | 942 | 477 | 222 | 297 | 1080 | 882 | 792 | 402 | 552 | 1662

## Slide 11: Among the various tasks, Project C comprised the highest number of tasks. Task ET2 was allocated the longest duration; however, it was task AT1 that actually consumed the most time. Analysis of the graph reveals that task BT2, CT3, CT5, DT1, and ET2 were completed in less time than initially allocated. Conversely, tasks AT2 and CT1 were accomplished within the assigned time frame. CT2 required the least amount of time compared to its budgeted hours, while ET2 and DT1 had the most significant negative impact on the scheduled hours. Notably, task AT1, BT2, CT1, DT1, and ET2 held the highest workload among all the tasks within Project A, B, C, D, and E, respectively. The consistent pattern of equal costs for each task was observed, influenced by the dependency on hourly wages. However, it is noteworthy that the highest costs were not only associated with tasks AT1 and ET2 but also with task DT1.

## Slide 12
Chart: Task cost
| AT1 | AT2 | AT3 | BT1 | BT2 | BT3 | CT1 | CT2 | CT3 | CT4 | CT5 | DT1 | DT2 | DT3 | DT4 | ET1 | ET2
ActualTotalCost | 142950 | 15600 | 9600 | 33300 | 58200 | 44100 | 63300 | 88200 | 44100 | 12600 | 35100 | 101400 | 70200 | 65700 | 34200 | 40200 | 98040
BudgetTotalCost | 129000 | 15600 | 9000 | 27000 | 60300 | 43800 | 63000 | 60600 | 45600 | 10200 | 36600 | 130800 | 67800 | 60600 | 31800 | 36600 | 137880

## Slide 13: Task count per personnel
Count of Task | Column Labels |  |  |  |  | 
Row Labels | Project A | Project B | Project C | Project D | Project E | Grand Total
Crystal |  |  |  | 4 | 1 | 5
Erica |  | 2 | 2 |  |  | 4
Gail | 3 | 2 | 2 |  | 1 | 8
George |  | 1 | 3 | 3 | 1 | 8
Inigo |  |  |  | 1 |  | 1
Jenny | 1 | 1 | 1 |  |  | 3
Jim | 1 |  |  | 1 |  | 2
Larry |  |  |  |  | 1 | 1
Monique | 2 | 1 | 1 |  |  | 4
Sarah |  |  |  | 2 |  | 2
Sondra |  |  |  |  | 1 | 1
Stanley | 1 | 2 | 4 | 3 | 2 | 12
Tom | 1 |  | 1 |  |  | 2
Grand Total | 9 | 9 | 14 | 14 | 7 | 53
Chart: 
| Crystal | Erica | Gail | George | Inigo | Jenny | Jim | Larry | Monique | Sarah | Sondra | Stanley | Tom
Project A | 3 | 1 | 1 | 2 | 1 | 1
Project B | 2 | 2 | 1 | 1 | 1 | 2
Project C | 2 | 2 | 3 | 1 | 1 | 4 | 1
Project D | 4 | 3 | 1 | 1 | 2 | 3
Project E | 1 | 1 | 1 | 1 | 1 | 2

## Slide 14: Observations and Key Insights
It is evident that Stanley and Crystal had the highest workload for projects C and D, respectively. Crystal, who is one of the highest-paid employees at $120 per hour, consistently performed well across a total of two projects. On the other hand, Stanley, despite his lower wage of $50 per hour, displayed exceptional performance by successfully managing tasks from all five projects, including the 12 tasks in total.
Based on this information, it can be concluded that Stanley is a highly proficient employee. Among the projects, C and D had the highest number of tasks assigned, while project E had the lowest, with only seven tasks.
It is worth noting that Inigo and Larry exhibited below-average performance, despite their above-average hourly pay. Both employees were assigned only one task and failed to meet expectations. As a result, their performance can be categorized as underwhelming.
In summary, the data highlights Stanley's exceptional performance and overall dedication, positioning him as a standout employee in the company. Crystal's consistent and accurate performance, coupled with her high hourly wage, reinforces her value to the organization. Meanwhile, Inigo and Larry's poor performance, despite their higher pay rates, indicates the need for improvement or reevaluation of their roles within the company.